## Functionality Audit
Dock AI — Complete Functionality & Dev Implementation Audit
Current scope: July 1 locked Product MD overrides older PRD conflicts. Status columns use Yes/No only.
Implemented = evidenced in dev logic/UI. No = not evidenced in reviewed material, not a code-level assertion. Known bugs make Working = No.
106 current-scope functions ¦ Implemented Yes: 48 ¦ Working Yes: 22 ¦ Ready: 22 ¦ Fix: 26 ¦ Build: 58
ID | Module | Functionality | Requirement reference | Dev implemented? | Observed working? | Launch action | Evidence / gap
F-001 | Product | Dock AI runs inside the existing FleetRobo LPA app with the same login/session. | Product MD §1; §3 D1 | Yes | Yes | Ready | Dock Operations is visible inside the existing LPA web application.
F-002 | Product | Current release is web-first. | Product MD §3 D8; §7.1 | Yes | Yes | Ready | Observed implementation is the web Dock Operations screen.
F-003 | Product | Bay allocation remains a human supervisor action. | Product MD §3 D2/D9; §4.2 | Yes | Yes | Ready | ALLOCATED state and existing allocation concept are present.
F-004 | Product | AI monitoring starts after bay allocation and camera association. | Product MD §1; §4.2; §6 | Yes | No | Fix | State logic supports Allocated, but Case 1 shows monitoring frequency did not adapt reliably.
F-005 | Product | Dock AI flow ends when the vehicle leaves the bay. | Product MD §1; §6 | Yes | No | Fix | Departure logic exists; Case 1 shows missed departures and incomplete journeys.
F-006 | Product | Inbound, outbound and secondary-dispatch workflows use the common AI event model. | Product MD §3 D10; §6 | No | No | Build | No implementation evidence for workflow-specific support or labels.
F-007 | Product | UI labels and downstream completion wording adapt by workflow type. | Product MD §3 D10; §6 | No | No | Build | Not present in the dev logic or reviewed UI evidence.
F-008 | Configuration | Camera and device identifiers map each AI event to a configured bay. | Product MD §2; §4.1; v4 §5 | Yes | No | Fix | Dev logic §4 implements mapping; Case 4 reports evidence mapped to the wrong dock.
F-009 | Configuration | Mapped online camera automatically enables AI for the bay. | Product MD §3 D3; §4.1; v4 §5 | Yes | Yes | Ready | AI events are processed for mapped bays in the dev logic and observed screens.
F-010 | Configuration | Mapped offline camera automatically moves the bay to Manual. | Product MD §3 D3; §4.3; v4 §5 | Yes | Yes | Ready | Dev logic §5: three camera failures set Manual and AI Offline.
F-011 | Configuration | Bay with no mapped camera operates in manual mode. | Product MD §3 D3; §4.1; v4 §5 | No | No | Build | Dev logic records an unmapped event but does not define the bay as manual.
F-012 | Configuration | Camera recovery resumes AI automatically without overwriting manual work. | Product MD §3 D4; v4 §4; PRD v1 §3.4/§3.8 | No | No | Build | Dev logic leaves Manual until communication and intervention are completed; timestamp preservation is unspecified.
F-013 | Configuration | Bay configuration exposes bay name/number, capacity, camera, camera status and AI mode. | Product MD §4.1; v4 §5 | No | No | Build | Bay number exists in operations UI; no complete configuration surface was evidenced.
F-014 | Configuration | Global AI camera settings exist in backend/admin. | Product MD §3 D12; §4.1/§4.4; v4 §6 | No | No | Build | No admin/config evidence reviewed.
F-015 | Configuration | Per-bay settings can override global settings. | Product MD §4.1; v4 §6 | No | No | Build | No override implementation evidence reviewed.
F-016 | Configuration | Configuration precedence is bay override → global default → system default. | Product MD §4.1; v4 §6 | No | No | Build | No precedence implementation evidence reviewed.
F-017 | Configuration | Required AI settings are changeable without code deployment. | Product MD §4.4; §3 D12 | No | No | Build | No configurable admin mechanism was evidenced.
F-018 | Configuration | Camera health is visible to operations/support. | Product MD §4.1; §4.9 | No | No | Build | Health exists as an event input but no operational/admin health UI was evidenced.
F-019 | Allocation | Supervisor selects vehicle and bay through the existing allocation flow. | Product MD §4.2; v4 §7 | Yes | Yes | Ready | Existing allocation concept and Allocated state are present.
F-020 | Allocation | Allocation confirmation stores the expected vehicle. | Product MD §4.2; v4 §7 | Yes | Yes | Ready | Dev logic uses the vehicle associated with an Allocated bay.
F-021 | Allocation | Allocation maps the operational session to the bay and camera. | Product MD §4.2; v4 §7 | Yes | No | Fix | Session/bay processing exists; Case 4 reports incorrect dock evidence mapping.
F-022 | Allocation | Allocation changes bay state to ALLOCATED. | Product MD §4.2/§4.3; v4 §§7-8 | Yes | Yes | Ready | ALLOCATED is implemented in the dev transition matrix.
F-023 | Allocation | Allocation starts the vehicle-arrival waiting timer. | Product MD §4.2; v4 §7 | Yes | No | Fix | Timers exist, but Bug 29665 shows a state timer stuck at its initial timestamp.
F-024 | Allocation | Allocation increases camera frequency to the pre-arrival interval. | Product MD §4.2/§4.4; v4 §§6-7 | No | No | Build | Case 1 explicitly reports unchanged inference frequency and missed events.
F-025 | Allocation | Vehicle-not-arrived threshold triggers a delayed-arrival exception. | Product MD §4.4/§4.8; v4 §6 | No | No | Build | No threshold or alert implementation evidence reviewed.
F-026 | AI Detection | Vehicle presence is detected at the bay. | Product MD §2; §4.3; PRD v1 §3.3 | Yes | Yes | Ready | Case 1 confirms arrival/presence was captured for Vehicle 1.
F-027 | AI Detection | Vehicle registration is detected when visible. | Product MD §2; §4.3; PRD v1 §3.3 | Yes | Yes | Ready | Registration is an AI input and evidence can contain a detected vehicle number.
F-028 | AI Detection | Detection confidence is captured with the event. | Product MD §4.6; v4 §9 | Yes | Yes | Ready | Dev logic §3 includes vehicle detection confidence.
F-029 | AI Detection | Detected plate is matched against the expected allocated vehicle. | Product MD §4.3; §6; v4 §7 | No | No | Build | Dev logic treats validated AI plate as source of truth instead of applying the required expected-vs-detected decision flow.
F-030 | AI Detection | Unreadable plate prompts YES or ENTER PLATE. | Product MD §4.3/§4.7/§4.8; v4 §7 | No | No | Build | No confirmation UI/action evidence reviewed.
F-031 | AI Detection | Wrong vehicle prompts ACCEPT HERE or REDIRECT. | Product MD §4.3/§4.7/§4.8; v4 §7 | No | No | Build | Dev logic auto-closes the old journey and swaps vehicles; required supervisor decision is missing.
F-032 | AI Detection | Low-confidence detection falls back to supervisor/manual confirmation. | Product MD §2; §3 D4; §4.8 | No | No | Build | Confidence is captured but no threshold-driven action is implemented.
F-033 | AI Detection | Invalid registration never silently attaches state changes to a stale vehicle. | Product MD §3 D4; §4.3; §6 | No | No | Build | Case 2 reports bay state changing while the vehicle number remains stale because registration validation is false.
F-034 | AI Detection | Bay capability supports absence of plate or door visibility. | Product MD §3 D4; §4.7; §6 | No | No | Build | Case 1 shows door status null and no visible plates; no capability-specific flow is defined.
F-035 | State Machine | Canonical current states are EMPTY, ALLOCATED, OCCUPIED, LOADING, LOADED and MANUAL. | Product MD §4.3; v4 §8 | Yes | No | Fix | All states exist, but multiple reported bugs show the displayed state diverging from stages/evidence.
F-036 | State Machine | Allocation confirmation transitions EMPTY → ALLOCATED. | Product MD §4.3; v4 §8 | Yes | Yes | Ready | Implemented in the dev transition model.
F-037 | State Machine | Confirmed vehicle arrival transitions ALLOCATED → OCCUPIED. | Product MD §4.3; §6; v4 §8 | Yes | No | Fix | Bugs 29664/29657 and Case 1 show missed or inconsistent Occupied state.
F-038 | State Machine | Door open with active vehicle transitions OCCUPIED → LOADING. | Product MD §4.3; §6; v4 §8 | Yes | No | Fix | Bug 29653 shows Loading started but Operation Stages did not update.
F-039 | State Machine | Stable door close after debounce transitions LOADING → LOADED. | Product MD §4.3; §6; v4 §8 | Yes | No | Fix | Bugs 29662/29655/29658/29660 show stuck or contradictory Loaded state.
F-040 | State Machine | Confirmed departure transitions LOADED → EMPTY. | Product MD §4.3; §6; v4 §8 | Yes | No | Fix | Case 1 shows missed departure/empty-bay transitions.
F-041 | State Machine | Camera offline transitions the affected bay to MANUAL. | Product MD §4.3; v4 §8 | Yes | Yes | Ready | Implemented in dev logic §5 and transition matrix.
F-042 | State Machine | AI service outage transitions all affected bays to MANUAL. | Product MD §4.3/§4.8; v4 §4 | No | No | Build | Dev logic covers per-camera failure only, not service-wide outage.
F-043 | State Machine | Every state transition records timestamp and trigger/history. | PRD v1 §3.2; Product MD §4.6 | Yes | Yes | Ready | Dev logic records events and state history.
F-044 | State Machine | Time in current state updates continuously. | Product MD §4.5; v4 §9 | Yes | No | Fix | Bug 29665: Occupied timer remains stuck at the initial timestamp.
F-045 | AI Settings | Idle screenshot/inference interval is configurable. | Product MD §4.4; v4 §6 | No | No | Build | No configuration evidence reviewed.
F-046 | AI Settings | Pre-arrival screenshot/inference interval is configurable. | Product MD §4.4; v4 §6 | No | No | Build | Case 1 reports unchanged frequency during rapid vehicle turnover.
F-047 | AI Settings | Active-vehicle screenshot/inference interval is configurable. | Product MD §4.4; v4 §6 | No | No | Build | No dynamic active-frequency implementation evidence reviewed.
F-048 | AI Settings | Confidence threshold is configurable. | Product MD §4.4; v4 §6 | No | No | Build | Confidence exists as data; no threshold configuration or action exists.
F-049 | AI Settings | Door-close debounce is configurable and enforced. | Product MD §4.4; §6; v4 §6 | Yes | No | Fix | Debounce is implemented in dev logic; Loaded-state bugs show unreliable end-state execution.
F-050 | AI Settings | Departure confirmation frame count is configurable and enforced. | Product MD §4.4; §6; v4 §6 | Yes | No | Fix | Two-frame rule exists; Case 1 shows departure capture still failing with current inference timing.
F-051 | AI Settings | Pre-loading idle threshold is configurable. | Product MD §4.4/§4.8; v4 §6 | No | No | Build | No threshold/alert implementation evidence reviewed.
F-052 | AI Settings | Post-loading idle threshold is configurable. | Product MD §4.4/§4.8; v4 §6 | No | No | Build | No threshold/alert implementation evidence reviewed.
F-053 | Loading | Door open captures loading/unloading start timestamp. | Product MD §2; §4.3; §6; v4 §7 | Yes | No | Fix | Dev logic captures start; Bug 29653 shows the stage not updating.
F-054 | Loading | Loading start timestamp is captured only once per activity. | PRD v1 §3.3; Dev logic §11 | Yes | Yes | Ready | Dev logic explicitly records start only once.
F-055 | Loading | Stable door close captures loading/unloading end timestamp. | Product MD §2; §4.3; §6; v4 §7 | Yes | No | Fix | Case 4 and Bug 29662 show missing Loading End/stuck Loading.
F-056 | Loading | Door reopening before completion returns/keeps the bay in LOADING. | Product MD §6; v4 §7 | No | No | Build | Dev logic waits for stable close but does not define the required visible re-open transition after Loaded evaluation.
F-057 | Loading | Loading completion marks the loading activity/task complete. | Product MD §6; v4 §7 | Yes | No | Fix | Bug 29660: bay is Loaded but vehicle pipeline does not reflect Loaded.
F-058 | Loading | Loading milestones update Operation Stages and vehicle pipeline consistently. | Product MD §4.6; §6 | Yes | No | Fix | Bugs 29653 and 29660 show inconsistent downstream stage updates.
F-059 | Departure | Departure timestamp is captured. | Product MD §6; v4 §7 | Yes | No | Fix | Case 1 shows a departure that was not reflected correctly.
F-060 | Departure | Post-loading idle and total bay time are calculated. | Product MD §6; v4 §7 | No | No | Build | No implementation evidence reviewed.
F-061 | Departure | Camera monitoring returns to idle frequency after departure. | Product MD §6; v4 §7 | No | No | Build | No dynamic frequency implementation evidence reviewed.
F-062 | Manual Fallback | Manual override remains available while AI is active. | Product MD §3 D4; §6; PRD v1 §3.8 | No | No | Build | No always-available override action was evidenced.
F-063 | Manual Fallback | Open-truck flow allows manual START LOADING and LOADING DONE. | Product MD §3 D4; §4.7/§4.8; §6 | No | No | Build | No open-truck manual action UI was evidenced.
F-064 | Manual Fallback | Camera-offline bay continues through manual operational actions. | Product MD §3 D3/D4; §4.7; §6 | No | No | Build | Manual state exists, but the operational manual flow/actions are not defined in the dev logic.
F-065 | Manual Fallback | AI-service-down condition provides global manual fallback. | Product MD §3 D4; §4.8; §6 | No | No | Build | No global service-down handling was evidenced.
F-066 | Manual Fallback | Supervisor can correct AI state/vehicle with a reason. | Product MD §3 D4; PRD v1 §3.2/§3.8 | No | No | Build | No correction action or reason capture was evidenced.
F-067 | Manual Fallback | Fallback uses one-tap current timestamp rather than primary date/time entry. | Product MD §4.7 | No | No | Build | Target fallback UX is not evidenced in the reviewed web implementation.
F-068 | Manual Fallback | AI recovery preserves manual timestamps and corrections. | Product MD §3 D4; PRD v1 §3.4/§3.8 | No | No | Build | Manual-data preservation on recovery is unspecified in dev logic.
F-069 | Alerts | Dock AI alerts use push notifications and in-app alerts only. | Product MD §3 D5; §4.8 | No | No | Build | No alert delivery implementation evidence reviewed.
F-070 | Alerts | Delayed-arrival alert triggers after allocation threshold. | Product MD §4.4/§4.8 | No | No | Build | No delayed-arrival alert evidence reviewed.
F-071 | Alerts | Pre-loading idle alert triggers before loading begins. | Product MD §4.4/§4.8; PRD v1 §3.5 | No | No | Build | No pre-loading idle alert evidence reviewed.
F-072 | Alerts | Post-loading idle alert triggers while loaded vehicle blocks bay. | Product MD §4.4/§4.8; PRD v1 §3.5 | No | No | Build | No post-loading idle alert evidence reviewed.
F-073 | Alerts | Wrong vehicle, unreadable plate and low-confidence alerts are generated. | Product MD §4.8 | No | No | Build | Dev logic auto-handles vehicle swap and does not expose required action alerts.
F-074 | Alerts | Camera-offline and AI-service-down alerts are generated. | Product MD §4.8 | No | No | Build | Camera state changes to Manual; no notification routing/action evidence exists.
F-075 | Alerts | User can acknowledge an alert and add structured reason/free text. | Product MD §4.8 | No | No | Build | No acknowledgement/reason UX evidence reviewed.
F-076 | Alerts | Alert action can accept vehicle here or redirect it. | Product MD §4.8 | No | No | Build | No wrong-vehicle action UI evidenced.
F-077 | Alerts | Alert action can manually start or complete loading. | Product MD §4.8 | No | No | Build | No manual loading action UI evidenced.
F-078 | Dashboard | Dock Operations presents a bay/dock tile grid. | Product MD §4.5; v4 §9 | Yes | Yes | Ready | Observed Dock Operations grid.
F-079 | Dashboard | Each tile shows bay/dock number. | Product MD §4.5; v4 §9 | Yes | Yes | Ready | Observed bay labels on tiles.
F-080 | Dashboard | Each tile shows canonical state and state color. | Product MD §4.5; v4 §9 | Yes | No | Fix | Bugs 29664/29662 report displayed state inconsistencies.
F-081 | Dashboard | Each tile shows time in current state. | Product MD §4.5; v4 §9 | Yes | No | Fix | Bug 29665 reports timer stuck at initial timestamp.
F-082 | Dashboard | Each tile shows vehicle plate when available. | Product MD §4.5; v4 §9 | Yes | No | Fix | Bug 29651 reports missing number despite arrival evidence.
F-083 | Dashboard | Each tile shows an alert marker when applicable. | Product MD §4.5; v4 §9 | No | No | Build | No alert marker evidence reviewed.
F-084 | Dashboard | Dashboard includes an Active Alerts section. | Product MD §4.5; v4 §9 | No | No | Build | No Active Alerts implementation evidence reviewed.
F-085 | Dashboard | Selecting a tile opens its detail panel/drawer. | Product MD §4.5; v4 §9 | Yes | Yes | Ready | Observed detail drawer on Dock Operations screen.
F-086 | Dashboard | Supervisor and Manager use the same screen with different visibility. | Product MD §4.5/§4.9 | No | No | Build | No role-scoped visibility evidence reviewed.
F-087 | Detail Drawer | Drawer shows session information. | Product MD §4.6; v4 §9 | Yes | Yes | Ready | Observed drawer with operational stages/session context.
F-088 | Detail Drawer | Drawer shows vehicle plate. | Product MD §4.6; v4 §9 | Yes | No | Fix | Bug 29651 reports missing vehicle number in bay details.
F-089 | Detail Drawer | Drawer shows existing order/reference context. | Product MD §4.6; v4 §9 | No | No | Build | No reliable implementation evidence reviewed.
F-090 | Detail Drawer | Drawer shows transporter when available. | Product MD §4.6; v4 §9 | No | No | Build | No implementation evidence reviewed.
F-091 | Detail Drawer | Drawer shows workflow type. | Product MD §4.6; v4 §9 | No | No | Build | No implementation evidence reviewed.
F-092 | Detail Drawer | Drawer shows session timeline/operation stages. | Product MD §4.6; v4 §9 | Yes | No | Fix | Bugs 29653/29660 and Case 4 report missing or stale stages.
F-093 | Detail Drawer | Drawer shows AI confidence and verification status. | Product MD §4.6; v4 §9 | No | No | Build | Confidence exists in events; required UI status was not evidenced.
F-094 | Detail Drawer | Drawer shows permission-based manual actions. | Product MD §4.6; v4 §9 | No | No | Build | No manual action controls evidenced.
F-095 | Detail Drawer | Drawer shows alert history and acknowledgement state. | Product MD §4.6; v4 §9 | No | No | Build | No alert history implementation evidence reviewed.
F-096 | Detail Drawer | Drawer shows AI snapshots/evidence when available. | Product MD §4.6; v4 §9 | Yes | No | Fix | Bug 29658 and Case 4 report missing evidence; other cases show incorrect dock evidence.
F-097 | Roles | Warehouse Supervisor/Manager can allocate and monitor docks. | Product MD §4.9; PRD v1 §2 | Yes | Yes | Ready | Allocation/dashboard surface exists, though permission enforcement was not independently tested.
F-098 | Roles | Dock/Loading user can manually start/end loading only for assigned docks. | Product MD §4.9 | No | No | Build | Manual actions and assignment checks were not evidenced.
F-099 | Roles | Transport/Dispatch user acts on loaded-but-not-moved alerts. | Product MD §4.9 | No | No | Build | Post-loading alert workflow was not evidenced.
F-100 | Roles | BSL Admin/Ops can manage configuration and camera health. | Product MD §4.9 | No | No | Build | No admin/config surface evidence reviewed.
F-101 | Roles | Manager/HO viewer can view all docks. | Product MD §4.9 | No | No | Build | Dashboard exists; role-specific access control was not evidenced.
F-102 | Roles | Existing role/session permissions control visibility and actions. | Product MD §2; §4.9 | No | No | Build | No permission-control evidence reviewed.
F-103 | Traceability | Every AI event is recorded before business processing. | PRD v1 §3.3; Dev logic §3 | Yes | Yes | Ready | Dev logic explicitly records each event before processing.
F-104 | Traceability | State history is stored for the vehicle journey. | PRD v1 §3.2; Dev logic §§2/13/15 | Yes | Yes | Ready | Dev logic stores state history and archives journey activity.
F-105 | Traceability | Evidence is linked to the correct bay, vehicle and session. | Product MD §4.6; v4 §9 | Yes | No | Fix | Case 4 reports evidence from a different dock; Bug 29651 shows identity not propagated.
F-106 | Traceability | Bay card, drawer, stages and vehicle pipeline use one consistent journey state. | Product MD §4.5/§4.6; §6 | Yes | No | Fix | Bugs 29664/29653/29660 show cross-surface state divergence.

## Excluded & Deferred
Dock AI — Explicit Exclusions & Deferred Scope
ID | Functionality | Current decision | Reference | Closure
S-001 | Separate Dock AI app/login | Out of current scope | Product MD §2; §3 D1 | Keep inside existing LPA app.
S-002 | Gate-in workflow redesign | Out of current scope | Product MD §2 | Existing gate-in remains unchanged.
S-003 | Gate-out workflow redesign | Out of current scope | Product MD §2 | Existing gate-out remains unchanged.
S-004 | Gate ANPR / boom barrier automation | Out of current scope | Product MD §2 | Bay cameras only.
S-005 | New SAP inbound/outbound APIs | Out of current scope | Product MD §2; §3 D7 | Use only context already available in LPA.
S-006 | Billing, PGI, GRN and invoice automation | Out of current scope | Product MD §2 | Existing downstream workflow remains.
S-007 | Parking-yard workflow | Out of current scope | Product MD §2; §3 D6 | Queue is not a new parking workflow.
S-008 | PA announcement system | Out of current scope | Product MD §2 | No PA integration in current delivery.
S-009 | TV/kiosk display | Not release-blocking | Product MD §2; §7.4 | Future/not committed.
S-010 | Analytics and value reports | Not release-blocking | Product MD §2; §7.4 | Capture data now; reports later.
S-011 | Safety/unsafe detection | Out of current scope | Product MD §2 | Separate product stream.
S-012 | Two-bay same-vehicle handling | Out of current scope | Product MD §2 | Advanced scenario deferred.
S-013 | PARKED / overnight state | Out of current scope | Product MD §2; §4.3; §5 | Overrides older PRD/v4 Parked state.
S-014 | Deep audit module | Not discussed yet | Product MD §2; §8 | Do not treat as current dev gap.
S-015 | Full edge-scenario catalogue | Not discussed yet | Product MD §2; §8 | Cases are being collected separately.
S-016 | Recovery playbook/model | Not discussed yet | Product MD §2; §8 | Do not treat as current committed functionality.
S-017 | Metrics/reporting module | Not discussed yet | Product MD §2; §8 | Not part of current launch audit.
S-018 | Queue/pipeline visibility | Next delivery | Product MD §3 D6; §7.3 | Visibility only after core dock screen is stable.
S-019 | Mobile Dock AI flow | Immediate next delivery | Product MD §3 D8; §4.7; §7.2 | Web current; mobile follows.
S-020 | Bay-map allocation replacing current flow | Future / not committed | Product MD §3 D9; §7.4 | Current allocation flow remains.
S-021 | Client-facing AI configuration UI | Later delivery | Product MD §3 D12; §7.3 | Backend/admin configuration first.
S-022 | Deep role-subprocess mapping [25141] | Skipped for current | Product MD §3 D11; §4.9 | Use existing permissions where available.
S-023 | Document links inside drawer | Lower priority | Product MD §4.6 | Not P0 unless already available.
S-024 | Pre/post checklist mobile prompts | Immediate next delivery | Product MD §4.7; §7.2 | Captured as mobile follow-up context.
S-025 | Mode B: AI discovers vehicles without allocation | Not in current locked flow | PRD v1 §3.1; Product MD §3 D2/D9 | Human allocation and existing flow override the older Mode B concept.
S-026 | Allocation auto-expiry that frees the bay | Not committed in current requirement | PRD v1 §3.1; Product MD §4.4 | Current scope keeps a vehicle-not-arrived threshold/alert, not confirmed auto-expiry.
S-027 | Bay reallocation redesign | Not committed as Dock AI change | PRD v1 §3.1; Product MD §3 D9 | Existing allocation flow remains; no replacement UX committed.
S-028 | Unknown/ad-hoc vehicle creation and automatic vehicle-swap workflow | Edge scenario deferred | PRD v1 §3.4; Product MD §2/§8 | Do not count as a current implementation gap until edge scenarios are locked.
S-029 | Broad alert re-fire, escalation chain and historical alert catalogue | Not in current alert pull | PRD v1 §3.5; Product MD §4.8 | Current requirement includes only operational alerts needed to keep bay flow moving.
S-030 | Dashboard filters, TV layout controls and advanced grid configuration | Not current P0 | PRD v1 §3.6/§5; Product MD §4.5 | Current P0 is tiles, alerts and detail drawer.
S-031 | Advanced data-retention configuration and failed-frame improvement store | Not current P0 / deep audit | PRD v1 §5; Product MD §2/§8 | Do not count as a current launch implementation gap.

## Defect Evidence
Dock AI — Reviewed Defect & Scenario Evidence
ID | Case / Bug | Observed issue | Affected functionality | Evidence source
D-001 | Case 1 | Arrival missed for Vehicle 2. | Arrival → OCCUPIED; inference frequency | Case 1 screenshot
D-002 | Case 1 | Departure not reflected correctly for Vehicle 1. | Departure → EMPTY | Case 1 screenshot
D-003 | Case 1 | Empty-bay state between Vehicles 2 and 3 was missed. | State transition / rapid turnover | Case 1 screenshot
D-004 | Case 1 | Door status is null because door is outside camera view. | Door-based loading detection | Case 1 screenshot
D-005 | Case 1 | No number plate visible for any vehicle. | ANPR fallback | Case 1 screenshot
D-006 | Case 2 | Bay state changes while registration is invalid and vehicle number remains stale. | Vehicle identity integrity | Gaurav debugging screenshot
D-007 | Case 2 | Door Open is followed directly by Vehicle Not Present; Door Close never arrives. | Loading completion / reconciliation | Gaurav debugging screenshot
D-008 | 29666 | Dashboard shows 12 vehicles while only 9 are physically present. | Bay count / journey closure | QA bug screenshot
D-009 | 29665 | Occupied timer remains stuck at initial timestamp. | Time in state | QA bug screenshot
D-010 | 29664 | Occupied bay does not display as Occupied when opened. | Card/detail state consistency | QA bug screenshot
D-011 | 29663 | False “Unable to load dock operations data” appears despite successful load. | UI error handling | QA bug screenshot
D-012 | 29662 | Bay remains “Loading Now” after vehicle is fully loaded. | LOADING → LOADED | QA bug screenshot
D-013 | 29651 | Vehicle number absent in details despite arrival evidence detection. | Identity propagation | QA bug screenshot
D-014 | 29653 | Loading started but Operation Stages does not update Loading Start. | Stage propagation | QA bug screenshot
D-015 | 29655 | Bay is Loaded while evidence indicates gate/door not closed. | Loaded evidence validity | QA bug screenshot
D-016 | 29657 | Bay is Occupied while evidence indicates gate/door inconsistency. | Occupied evidence validity | QA bug screenshot
D-017 | 29658 | Loaded state has no evidence image. | Evidence capture | QA bug screenshot
D-018 | 29660 | Bay is Loaded but vehicle pipeline does not reflect Loaded. | Pipeline propagation | QA bug screenshot
D-019 | Case 4 | Camera/evidence appears mapped to a different dock. | Camera-to-bay mapping | Dock Operations conversation screenshot
D-020 | Case 4 | Dock 4 stays Loading for ~4 hours because Loading End is absent. | Loading-end timeout/recovery | Dock Operations conversation screenshot
D-021 | Case 4 | Dock 12 tile has state/vehicle but stages and evidence are missing. | Card/detail/session consistency | Dock Operations conversation screenshot